User Guide

for

Standard Bidding Document

for the

Procurement of Works

by

International Competitive Bidding

Republic of Malawi

June 2005

Table of Contents

Acronyms	3

Guidance Notes on the use of Standard Bidding Documents and the User Guide	4

Purpose of the Standard Bidding Document	4

Purpose of the User Guide	4

When to Use the Standard Bidding Document for Works	4

Structure of the Standard Bidding Document	5

Rules for drafting Bidding Documents	6

Summary of the Bidding Process	7

Guidance Notes for the preparation of Invitation to Bid Notices or Letters	8

Invitation to Bid Notices	8

Invitation to Bid Letters	10

Guidance Notes on the Preface Section	12

Guidance Notes on Section 1. Instructions to Bidders	13

Guidance Notes on Section 2. Bid Data Sheet	14

Guidance Notes on Section 3. Evaluation and Qualification Criteria	19

1. Qualification Criteria	19

2. Domestic Preference	20

Guidance Notes on Section 4. Bidding Forms	22

Guidance Notes on Section 5. Eligible Countries	23

Guidance Notes on Section 6. Schedule of Requirements	24

Scope of Works	24

Technical Specifications	25

Drawings	26

Bill of Quantities or Activity Schedule	26

Guidance Notes on Section 7. General Conditions of Contract	31

Guidance Notes on Section 8. Special Conditions of Contract	32

Additional Optional Clauses	38

Guidance Notes on Section 9. Contract Forms	41

Agreement	41

Performance Security and Advance Payment Security	41

Guidance Notes on the Notice of Acceptance	45

Annex 1: Sample Bill of Quantities	46

Acronyms

BDS	Bid Data Sheet

BD	Bidding Document

BOQ	Bill of Quantities

EQC	Evaluation and Qualification Criteria

GCC	General Conditions of Contract

FIDIC	International Federation of Consulting Engineers

ITB	Instructions to Bidders

PE	Procuring Entity

SBD	Standard Bidding Document

SCC	Special Conditions of Contract

SOR	Schedule of Requirements

Guidance Notes on the use of Standard Bidding Documents and the User Guide

Purpose of the Standard Bidding Document

The purpose of the SBD is to provide Procuring Entities (PEs) with one standard draft containing basic contractual provisions and safeguards which are required by the Government of the Republic of Malawi in the execution of public procurement and the use of public funds.

The Standard Bidding Document for the Procurement of Works has been designed to:

(i)	simplify the drafting of a specific bidding document for Procurement of Works by procurement staff;

(ii)	minimise the time required by the Internal Procurement Committee to approve Bidding Documents prior to release;

(iii)	reduce Bidders’ time and effort in the preparation of Bids; and

(iv)	facilitate and simplify the evaluation and comparison of bids and Contract award by the Procuring Entity.

The key feature of the SBD is that it can be used with minimum changes, as it does not contain explanations, footnotes or examples that should not form part of the Bidding Document.

Purpose of the User Guide

This User Guide has been prepared to provide guidance to public officials in the correct use of the Standard Bidding Documents (SBD) for Works as a model for preparing an individual Bidding Document (BD).

Users should ensure that the correct User Guide is referred to. Different User Guides have been produced for each SBD including those for the Procurement of Works by National Competitive Bidding (NCB), Minor Works, Small Works and for Goods and Services. Users should refer to the header and footer of each page of the User Guide to ascertain this.

The SBD contains guidance notes for Bidders (or Financial Institutions) only, which are mainly in Sections 4 and 9. These notes should not be deleted from the Bidding document when drafting.

All the explanations and notes necessary for PEs to use the SBD are contained in this User Guide.

All guidance notes, in both the bidding document and the user guide, are found between square brackets in bold e.g. [insert general description of works].

This User Guide is not part of the Bidding Document and is not intended for issue to Bidders.

When to Use the Standard Bidding Document for Works

Procurement Method

This SBD for the Procurement of Works by International Competitive Bidding is suitable for use under Open Tendering, either with or without pre-qualification. It is also suitable for use under Restricted Tendering.

Type of Contract

This Document can be used when the Procuring Entity intends to place either an Admeasurement contract (with a Bill of Quantities) or a Lump Sum contract (with an Activity Schedule). It is essential that the type of contract is specified in the Bid Data Sheet and Special Conditions of Contract in Sections 2 and 8 of the Bidding Document.

Admeasurement contracts are generally more appropriate for roads, larger buildings and other forms of construction where the quantities of work inputs required cannot be precisely defined at the planning stage and are subject to change in quantity or specifications resulting from site conditions.

Lump sum contracts should be used wherever practical for buildings and works that can be accurately quantified prior to construction.

Scope and Value of Contract

This SBD is suitable for a standard contract, where the works have been fully designed by or for the Procuring Entity, prior to bidding, and the Contractor will be responsible for construction only for works estimated to cost up to MWK 1 billion.

This SBD is not recommended for the following situations:

- specialist complex works under MWK1 billion, such as large water treatment plants;

- works estimated to cost over MWK1 billion;

- works designed by the Contractor, including turnkey contracts.

For any of these requirements, the Procuring Entity should use an alternative, more appropriate document, such as the internationally respected FIDIC standard forms of contract.

Structure of the Standard Bidding Document

The SBD is divided into nine separate Sections and a Preface. Procuring Entities are required to use all Sections of the Standard Bidding Document to produce an individual Bidding Document for issue to Bidders. The Standard Bidding Document comprises:

Preface

Part 1	Bidding Procedures

Section 1. 	Instructions to Bidders (ITB)

Section 2. 	Bid Data Sheet (BDS)

Section 3. 	Evaluation and Qualification Criteria (EQC)

Section 4. 	Bidding Forms

Section 5. 	Eligible Countries

Part 2	Schedule of Requirements

Section 6. 	Schedule of Requirements

Part 3	Contract

Section 7. 	General Conditions of Contract (GCC)

Section 8. 	Special Conditions of Contract (SCC)

Section 9. 	Contract Forms

- Each section is provided as a separate electronic document, removing the difficulties of drafting long documents. Collation of the sections is accomplished by reading the preface (5 pages) and manually inserting the relevant sections into each part of the preface pages.

Rules for drafting Bidding Documents

- It is important that Procuring Entities always use the original Standard Bidding Document to commence drafting a new Bidding Document for each new procurement requirement. Therefore, the original SBD should not be amended in any way.

- The SBDs have been designed to require the minimum of input or changes to the document so that a final Bidding Document can be produced with minimum time and effort.

- Most importantly the provisions in

- Section 1 	Instructions to Bidders and

- Section 7 	General Conditions of Contract

- must be used with their text unchanged.

- Any data or information that Sections 1 or 7 require are to be included respectively in

- Section 2 	Bid Data Sheet and

- Section 8 	Special Conditions of Contract

- Data and information contained in the remaining Sections should be modified as follows:

- Section 3 	Evaluation and Qualification Criteria This section must be completed with details of any evaluation criteria, and the qualification criteria, to be applied, where a pre-qualification has not been conducted. Examples are provided in this User Guide.

- Section 4 	Bidding Forms The Forms in this section are to be completed by the Bidder. No changes to the standard forms should be made by the PE.

- Section 5 	Eligible Countries A standard wording is included for Government funded procurement. Changes may be made where the procurement is subject to donor rules or where the Government has introduced any different or additional rules on eligibility.

- Section 6 	Schedule of Requirement This section should be completed with technical details of the works required, through a scope of works, technical specifications, drawings and a bill of quantities or activity schedule.

- Section 9	Contract Forms Procuring Entities are required to include the Contract Form in the Bidding Document. Details do not need to be completed until the contract award stage.

- This User Guide contains a section corresponding to each section of the SBD. It also includes an initial section on how to prepare the Invitation to Bid Notice or letter and a section at the end on preparing a Notice of Acceptance.

- In drafting Bidding Documents using the SBDs, users should not:

- delete any Section or page breaks,

- make any changes to the headers of the SBD,

- make any changes to the footers of the SBD.

Summary of the Bidding Process

- The Public Procurement Law, 2003 and the Public Procurement Regulations, 2004 detail the full procurement processes, rules and procedures and the procurement methods to be followed by Procuring Entities. The Law and Regulations must be complied with at all times.

- The activities within the bidding process are summarised here as follows:

- Selection of Bidders;

- Preparation and Issue of Bidding Documents;

- Bidding Period and Bid Receipt;

- Bid Opening;

- Bid Evaluation; and

- Bid Acceptance, Contract Award and placement.

- Full details of the procedures to be adopted in the bidding, evaluation, and contract award processes are contained in the following desk instructions:

1	Raising a requisition

2B	Preparing a description of requirements for works

3	Selecting the procurement method and planning the procurement

4A	Conducting a pre-qualification

5A	Preparing an invitation to tender notice

5B	Developing a short list

6A 	Drafting a bidding document or request for proposals document

7	Publishing an invitation to tender notice

8	Issuing invitation documents

9	Managing a pre-bid conference and site visits

10	Handling bidder clarifications, modifications and extensions

11	Receiving tenders

12A	Opening tenders

13	General evaluation procedures for works

13B	Evaluating offers for works

15	Conducting post-qualification

16	Conducting negotiations

17	Cancelling procurement proceedings

18	Issuing a notice of acceptance

19A	Preparing and issuing a contract document

20	Publishing a contract award notice and debriefing unsuccessful bidders

Guidance Notes for the preparation of Invitation to Bid Notices or Letters

Invitation to Bid Notices

- Invitation to Bid Notices must be published under the Open Tendering method, unless a pre-qualification has been conducted. They are designed to provide information that enables potential bidders to decide whether to participate in a bidding process. Apart from the essential items listed in the draft below, the Invitation to Bid Notice should also indicate any important bid evaluation criteria (for example, the application of a margin of preference in bid evaluation) or qualification requirements (a minimum level of turnover or experience).

- The Invitation to Bid Notice is for publication purposes only and is not a part of the Bidding Documents.

Standard Format for Invitation to Bid Notices

# [Brief Description of the Works]

[Procurement Reference number]

1.	The [insert name of Procuring Entity] has budgeted public funds to be used for the procurement of the works specified below, and now invites sealed bids from eligible bidders for the provision of. [insert description of works to be procured1,2]

2.	Bidding will be conducted in accordance with the open tendering procedures contained in the Public Procurement Law and Regulations of the Government of Malawi and is open to all bidders from eligible source countries. A bidder shall be required to obtain a certificate of registration from the National Construction Industry Council demonstrating registered supplier status, as a condition of contract award 3

3.	Interested eligible bidders may obtain further information from [insert name of Procuring Entity] and inspect the bidding documents at the address given below at 6(a) from [insert office hours]. 4

4.	A complete set of Bidding Documents in English may be purchased by interested bidders application to the address below at 6(b) and upon payment of a non-refundable fee5 of [insert amount in Malawi Kwacha] or [insert amount in specified convertible currency]. The method of payment will be [insert method of payment] 6. The document may be collected, or will be sent by [insert delivery method]. No liability will be accepted for loss or late delivery.

5.	Bids must be delivered to the address below at 6(c) at or before [insert time and date]. [If appropriate, include the following: All bids must be accompanied by a bid security of (insert percentage) percent of the total bid price].7 Late bids shall be rejected. Bids will be opened in the presence of the bidders’ representatives who choose to attend at the address below at 6(d) at [insert time and date] 8.

6.	(a)	Address documents may be inspected at:	[Insert address and contact details]

(b)	Address documents will be issued from:	[Insert address and contact details]

(c)	Address Bids must be delivered to:		[Insert address and contact details]

(d)	Address of Bid Opening:			[Insert address and contact details]

Notes

1. 	A brief description of the Works should be provided, including the location of the project, and other information necessary to enable potential bidders to decide whether to respond to the invitation. If Bidding Documents require bidders to have specific experience or capabilities, such restrictions should also be included in this paragraph.

2. 	[Insert if applicable]. The required completion period is [insert no. of days/months/years or dates].

3. 	Occasionally, contracts may be financed out of donor funds that would restrict eligibility to particular countries. If this is the case, it should be mentioned in this paragraph. Also indicate any margin of preference that may be granted as specified in the Bidding Documents. Note also that a successful bidder is required to obtain a certificate of registration from the National Construction Industry Council demonstrating registered Contractor status, as a condition of contract award. Bidders should be encouraged to seek this registration prior to bidding to avoid delays in the contract award process.

4.	For example: 09:00 to 12:00 hours.

5. 	The fee, to defray printing and mailing/shipping costs, should be nominal. If no fee is to be charged ensure that this is stated.

6. 	For example, cashier’s cheque, direct deposit to specified account no., etc.

7. 	The amount of bid security should be stated as a percentage based on 1-3% of the total bid price. Alternatively, if a bid security is not required, the paragraph should so state.

- The place for bid opening may not necessarily be the same as that for issuance of documents or for bid submission. If they differ, each address must appear in paragraph 6 and be numbered. The text in the paragraph would then refer to address (1), (2), etc. Only one place and its address may be specified for submission, and it should be near the place where bids will be opened. Addresses should not be PO Boxes where physical submission or collection of a document is required.

- Any further information relating to the proposed bidding process, such as the intention to hold a pre bid meeting should also be included as appropriate.

Invitation to Bid Letters

- Invitation to Bid letters are issued to shortlisted bidders under Restricted Tendering or where bidders have been pre-qualified. They are used to invite specific Bidders who are felt to have the prerequisite skills, capacity or qualifications to fulfil a requirement and are already registered with the National Construction Industry Council.

- The Invitation to Bid Letter is not a part of the Bidding Documents.

Standard Format for Invitation to Bid Letters

Letterhead paper with PE name and address

[Name and address of selected Bidders – list all Bidders]

[Procurement Reference number]

[Date]

Dear Sirs,

Invitation to Bid for [Brief Description of the Works]

1.	The [insert name of Procuring Entity] has budgeted public funds to be used for the construction of the above referenced Works.

2.	The [insert name of Procuring Entity] invites sealed bids from eligible/pre-qualified [delete as applicable] bidders for the provision of these Works. 1,2

3.	Bidding will be conducted in accordance with the open/restricted [delete as applicable] tendering procedures contained in the Public Procurement Law and Regulations of the Government of Malawi. Bidding is open to the Bidders listed above from eligible source countries.3

4.	A complete set of Bidding Documents in English is attached.

5.	Bids must be delivered to the address below at 6(b) at or before [insert time and date]. [If appropriate, include the following: All bids must be accompanied by a bid security of (insert percentage) of the total bid price].4 Late bids shall be rejected. Bids will be opened in the presence of the bidders’ representatives who choose to attend at the address below at 6 (c) at [insert time and date].5

6	(a)	Address Bids must be delivered to:		[Insert street address]

(b)	Address of Bid Opening:			[Insert street address]

Yours sincerely,

[Insert name of office and name of officer]	[Insert postal/street address]

Notes

1. 	A brief description of the Works should be provided, including the location of the site and other information necessary to enable potential bidders to decide whether to respond to the invitation. If Bidding Documents require bidders to have specific experience or capabilities, such restrictions should also be included in this paragraph.

2. 	[Insert if applicable]. The completion period is [insert no. of days/months/years or dates].

3. 	Occasionally, contracts may be financed out of donor funds that would restrict eligibility to particular countries. If this is the case, it should be mentioned in this paragraph. Also indicate any margin of preference that may be granted as specified in the Bidding Documents.

4.	The amount of bid security should be stated as a percentage based on 1% - 3% of the estimated cost of the works. Alternatively, if a bid security is not required, the paragraph should so state.

5. 	The place for bid opening may not necessarily be the same as that for bid submission. If they differ, each address must appear in paragraph 6. Only one place and its address may be specified for submission, and it should be near the place where bids will be opened.

- It should be noted that the Invitation to Bid Letter is addressed to all Bidders that have either pre-qualified or have been selected for restricted tendering so that each Letter indicates the names of all Bidders that have been invited to bid.

Additional information, such as details of any pre-bid meeting should also be included in the invitation to bid letter.

Guidance Notes on the Preface Section

This Section of the Standard Bidding Document comprises five pages of which the first two pages are the cover sheets to the Bidding Document and the remaining three pages are separators or dividers for the three Parts of the Document. Only the first page of the Preface requires any inputs or text changes as illustrated below.

{Entity or Project Crest or Logo}

Republic of Malawi

{Name of Procuring Entity and/or Project}

Bidding Document

for the

Procurement of Works

by

International Competitive Bidding

Subject of Procurement:	[Insert general description of works to be procured].

Procurement Reference 	[Insert the Procurement Reference number for this

Number:	procurement]

Procurement Method:	[Insert Open/Open International/Restricted Tendering as appropriate]

Date of Issue of Bidding:	[Insert official issue date of the Bidding Document]

Document

Guidance Notes on Section 1. Instructions to Bidders

- The Instructions to Bidders (ITB) inform Bidders of the procedures that regulate the bidding process. The ITB contain standard provisions that have been designed to remain unchanged and to be used without modifying their text. The ITB clearly identify the provisions that may normally need to be specified for a particular bidding process and require that such details be introduced through the BDS.

- Conventionally the Instructions to Bidders contain information and data relating to the procedure for bidding and evaluation up to the point of contract award. Matters that will govern the performance of the Contractor, payment under any resulting contract or the rights and obligations under any resulting contract are contained in Section 7, 8 and 9, the General and Special Conditions of Contract and the Agreement. If duplication of a subject is inevitable in the different Sections of the document, care must be exercised to avoid contradiction between clauses dealing with the same matter(s).

- The Instructions to Bidders are not a Contract document and, therefore, will not form a part of any eventual Contract.

Guidance Notes on Section 2. Bid Data Sheet

The Bid Data Sheet (BDS) contains information and provisions that are specific to a particular bidding process. The Procuring Entity must specify in the BDS the information that the ITB indicates should be specified in the BDS.

The BDS must always be prepared with reference to the actual ITB clauses to ensure that the two sections are fully compatible in content and meaning.  The BDS must contain a corresponding clause where the ITB states “as specified (or indicated) in the BDS”.  If the ITB states “unless otherwise specified in the BDS” and the required terms are already stated in the ITB, it is preferable that no entry appears in the BDS.  However, to ensure that these Clauses are not overlooked during preparation of the BDS, they are included in the draft document and User Guide with an optional wording for accepting the ITB clause or entering an amendment.

To facilitate the preparation of the BDS, the clauses are numbered with the same numbers as the corresponding ITB clause.  This Guide provides information to the Procuring Entity on how to enter all required information, and includes a BDS format that summarises all information to be provided.

- The BDS must be prepared by the PE prior to the issue of the Bidding Document.

- The Bid Data Sheet is not a Contract document and, therefore, will not form a part of any eventual Contract.

Input of Information to be completed by Procuring Entity

Section 2. Bid Data Sheet

| Instructions to Bidders (ITB) reference | Data relevant to the ITB |
| --- | --- |
| A. General |  |
| ITB 4.6 and ITB 30.1 | A margin of preference [insert “will” or “will not”] apply. Where a margin of preference applies, the criteria for eligibility and the appropriate application methodology are described in Section 3, Evaluation and Qualification Criteria. |
| ITB 7.2 | The Procuring Entity [insert “will” or “will not”] hold a pre-bid meeting and/or site visit [delete as applicable]. [For major contracts, it is good practice for the Procuring Entity to organise a pre-bid meeting, which provides the opportunity of providing information and a session for questions and answers. If possible, the meeting should include a site visit.] If a pre-bid meeting and/or site visit is being held, it shall take place at: Location: [insert full address for pre-bid meeting]. Date: [insert day, date, month and year of pre-bid meeting e.g. Monday 15th November 2005] Time: [insert time and identify if a.m. or p.m. e.g. 11.00 a.m.] |
| B. Bidding Documents |  |
| ITB 9.1 | clarification purposes only, the Procuring Entity’s address is: - Attention: [insert full name of contact person] - Street Address: [insert street address and number] - Floor/Room number: [insert floor and room number, if applicable] - Town/City: [insert name of city or town] - PO Box No/Postal Code: [insert postal, or PO Box No if applicable] - Country: [insert Malawi] - Telephone: [insert number, inc. country/city codes] - Facsimile number: [insert number, inc. country/city codes] Email address: [insert email address, if applicable] |
| C. Preparation of Bids |  |
| ITB 12.1(f) | The Bidder shall submit with its bid the following additional documents or information: [insert any other documents required] |
| ITB 13.1 | The contract is an Admeasurement/Lump Sum [delete as applicable, ensuring that the contract type is the same as in clause 37.1 of the Special Conditions] Contract. |
| ITB 13.5 | Bid prices [insert “shall” or “shall not”] be subject to adjustment during performance of the contract. |
| ITB 14.2 | The authority for exchange rates shall be [insert source of exchange rates e.g. Reserve Bank of Malawi]. |
| ITB 15.1 and ITB 22.4 | Bids shall remain valid for [insert number] days. [The period must be sufficient for the Procuring Entity to evaluate bids, obtain all approvals and award a contract. Usually this is expressed as 60, 90 or 120 days. A minimum of 60 days is normally used, with up to 120 days for high value and complex works requiring detailed evaluation.] |
| ITB 15.3 | Any adjustment of Bid price for extensions of bid validity beyond 60 days shall be calculated on the basis of an annual increase for foreign costs of [insert percentage] percent and an annual increase for local costs of [insert percentage] percent. [The rates inserted should reflect the current rates of inflation internationally and in Malawi but should be reasonably equitable] |
| ITB 16.1 | The amount of the bid security shall be [insert percentage] percent of the total bid price in Malawi Kwacha or the equivalent in a freely-convertible currency. |
| ITB 17.1 | Alternative proposals to the requirements of the bidding documents [insert “will” or “will not,” as appropriate] be permitted with respect to [describe the alternatives to be permitted, or delete, as appropriate]. [Alternatives must be considered on a case by case basis. Alternatives could apply to certain parts of the works e.g. the use of structural steel in place of reinforced concrete. Often Contractors wish to propose alternatives because they own specialised equipment or expertise for alternative construction methods, which may offer cost savings. Where it is considered that there are viable alternatives, alternative bids should be permitted.] [If alternatives may be considered, insert either: “A bidder may submit an alternative bid only with a bid for the original specification. The Procuring Entity shall only consider the alternative bids offered by the Bidder whose bid for the original specification was determined to be the lowest-evaluated bid.” or “ A bidder may submit an alternative bid with or without a bid for the base case. The Procuring Entity shall consider bids offered for alternatives as specified in the Schedule of Requirements. All bids received, for the original specification, as well as alternative bids meeting the performance requirements, shall be evaluated on their own merits in accordance with the same procedures, as specified in ITB 29.”] |
| ITB 18.1 | In addition to the original of the bid, the number of copies is: [insert number, usually two, but more if essential] copies. |
| D. Submission of Bids |  |
| ITB 19.2(a) | For bid submission purposes only, the Procuring Entity’s address is : Attention: [insert full name of contact person] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] Town/City: [insert name of city or town] PO Box No/Postal Code: [insert postal code, if applicable] Country: [insert Malawi] |
| ITB 19.2(b) | The Procurement Reference Number is [insert Procurement Reference Number] |
| ITB 20.1 | The deadline for bid submission is: Date: [insert day, date, month, and year, e.g. Monday 15 November, 2005] Time (local time): [insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.] |
| ITB 23.1 | The bid opening shall take place at: Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] Town/City: [insert name of city or town] Country: [insert Malawi] Date: [insert day, date, month, and year, e.g. Monday 15 November, 2004] Time (local time): [insert time, and identify if a.m. or p.m. e.g. 11:00 a.m.] |
| F. Award of Contract |  |
| ITB 35.1 | The Adjudicator proposed by the Procuring Entity is [insert name and address]. The hourly fee for this proposed Adjudicator shall be [insert currency and amount]. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. [Attach relevant information, such as education, experience, age, nationality, and present position]. [The appointment of the Adjudicator requires care and attention. The Adjudicator should be of an appropriate professional discipline and have knowledge and experience of resolving contract disputes, either in the Project Manager, Adjudicator or Arbitrator role. The Contractor has the option of proposing an alternative Adjudicator at the bid stage, which in turn the Procuring Entity has the prerogative of accepting or declining at the acceptance stage. If the Procuring Entity does not accept the Adjudicator proposed by the Contractor, the Appointing Authority designated in the SCC selects the Adjudicator.] [For smaller contracts, the Procuring Entity may decide not to appoint an Adjudicator, in which case, the text should be replaced with “No Adjudicator is to be appointed under this contract”. Where no Adjudicator is to be appointed, the Procuring Entity must also make appropriate amendments to the relevant Special Conditions of Contract]. |

Guidance Notes on Section 3. Evaluation and Qualification Criteria

The purpose of the Evaluation and Qualification Criteria (EQC) is to inform Bidders of the criteria that the Procuring Entity will use to evaluate the bids and post-qualify the bidder submitting the lowest evaluated bid. This is to ensure that the evaluation is fair and treats all Bidders in the same manner. It also should assist Bidders to prepare responsive bids which meet the PE’s needs and are competitive. The Procuring Entity must prepare the EQC and include it as a part of the Bidding Documents.

The EQC is not a Contract document and, therefore, it is not a part of any eventual Contract.

Section 3 of the SBD requires criteria to be added in two main areas, relating to:

- qualification criteria; and

- the application of a margin of preference for domestic Contractors.

Guidance is provided below on the completion of each of these sections. Example criteria are provided, but the criteria must be prepared for each individual requirement, depending on the value of the potential bids, the complexity of the assignment, the details of any domestic preference scheme etc.

1. Qualification Criteria

This part must be drafted in conjunction with the standard instructions in Section 1, Instructions to Bidders. It is used to modify the standard instructions and to provide figures and other details for the qualification criteria, which are appropriate to the particular works contract.

Where a pre-qualification has been conducted, the standard wording in this part should be deleted and replaced with “Not applicable. Pre-qualification information will be verified in accordance with ITB Clause 4.2”.

Where no pre-qualification has been conducted, the standard wording should be completed as shown below. The criteria can be amended or deleted, if appropriate, and further criteria can be added as required.

The information required from bidders in ITB Sub-Clause 4.3 is modified as follows: [list any additions or deletions to the list of information and documents in ITB Sub-Clause 4.3 or state “no modifications”].

The requirements for joint ventures in ITB Sub-Clause 4.4 are modified as follows: [list any additions or deletions to the requirements in ITB Sub-Clause 4.4 or state “no modification”].

To qualify for award of the Contract, in accordance with ITB Sub-Clause 4.5, bidders shall meet the minimum qualifying criteria: [complete the details required for the criteria at (a) to (e) below or delete or amend. Additional criteria may be added if required]

(a)	average annual volume of construction work over the past [insert number of years. For major contracts, it is normally 5 years, for smaller contracts 3 years would be sufficient] of at least [insert currency and amount. Ideally the minimum value of the annual turnover of construction work should be set at not less than 2.5 times the estimated annual cash flow for the Contract. For low risk works, this minimum could be reduced to 2 times or less]

(b)	experience as prime contractor in the construction of at least [insert required number of similar contracts, which should be in the range of one to three, depending on the size of contract, risk of Contractor default and market conditions]works of a nature and complexity equivalent to the Works over the last _____ [insert number of years, normally in the range of five to ten. For smaller contracts, low risk works, or a newly established local industry, the number of years could be reduced to 3] years (to comply with this requirement, works cited should be at least seventy (70) percent complete);

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: [insert list of equipment. For smaller contracts, the list should be limited to specialised items that are critical to the execution of the contract and that may be difficult for the successful Bidder to obtain quickly]

(d)	personnel with the following qualifications and experience: [insert qualifications and experience required for key personnel e.g. “a Contract Manager with five years’ experience in works of an equivalent nature and volume, including no less than three years as Manager”. Personnel requirements should be limited to key site management and technical personnel, who will be responsible for major components e.g. site superintendents, contract manager etc]

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than [insert amount. The successful Bidder must demonstrate that it has or has access to the financial means sufficient to meet the construction cash flow requirements for the contract. The minimum liquid assets and credit should normally be set as the estimated payment flow over approximately 3 months at the average (“straight lined”) construction rate.];

A consistent history of litigation or arbitration awards against the Applicant or any partner of a Joint Venture may result in disqualification.

The figures for each of the partners of a joint venture shall be added together to determine the Bidder’s compliance with the minimum qualifying criteria in (a) and (e) above; however, for a joint venture to qualify, each of its partners must meet at least twenty-five (25) percent of minimum criteria (a), (b), and (e) above for an individual Bidder, and the partner in charge at least 40 percent of those minimum criteria. Failure to comply with this requirement will result in rejection of the joint venture’s Bid.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria. [amend if required].

2. Domestic Preference

Detailed procedures for the application of the margin of preference must be inserted here, in accordance with ITB Clauses 4.1 and 30.1, if so specified in the SCC.  A sample wording for the qualification criteria and the method of applying domestic preference during the evaluation process is included in the BDS.  The method of applying domestic preference for works is stated in the Public Procurement Regulations, 2004 and should not be altered.  The qualification criteria for domestic preference are not stated in the Regulations and the wording may be further modified to reflect any directives issued by the Office of the Director of Public Procurement.

Note that if a margin of domestic preference is to be granted to qualifying bidders, any specific documentary evidence required to confirm a Bidder’s eligibility must be formally requested within this section.

If a margin of domestic preference will not be applied to this procurement process, the whole text under “2 Domestic Preference” should be deleted, and the wording “No margin of domestic preference will be granted.” inserted.

Guidance Notes on Section 4. Bidding Forms

The Procuring Entity must include all bidding forms that the Bidder must complete and include in its bid in the Bidding Document. As specified in Section 4 of the Bidding Document, these forms are the Bid Submission Form, the Priced Schedules (Bill of Quantities or Activity Schedule, depending on the type of contract), the Bid Security Form and the Qualification Information form.

As the Bidder (or a financial institution in the case of the Security) is required to complete these Forms, guidance notes are included on the forms (in bold between square brackets) in the SBD. These guidance notes should not be deleted by the Procuring Entity prior to the issue of the Bidding Document. The Procuring Entity is not required to input or change any information in Section 4.

This User Guide is not intended for Bidders as all information that the Bidder is required to provide should be detailed by the Procuring Entity in the Bidding Document. The forms in Section 4, complete with guidance notes, are not therefore included in this User Guide.

Guidance Notes on Section 5. Eligible Countries

Section 5 specifies the countries from which bidders (including subcontractors or suppliers) are eligible. Section 5 is not a contract document.

Section 5 of the SBD includes the following wording, which will normally apply to any Government funded contract:

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

(a)	as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

(b)	by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

The list of eligible countries may differ, where the procurement is funded by a donor or where other restrictions are imposed by Government policy. In such cases, the Procuring Entity should amend the text accordingly, inserting either a list of eligible countries or a list of ineligible countries. The list of countries should be checked directly with the Government or donor.

Guidance Notes on Section 6. Schedule of Requirements

The Schedule of Requirements (SOR) must inform Bidders of precisely of the works required by the Procuring Entity. The Schedule of Requirements must provide sufficient information to enable bidders to efficiently and accurately prepare bids that are realistic, competitive and responsive. The SOR must be prepared by suitably qualified and experienced staff and the assistance of professional specialists (architects, civil engineers and quantity surveyors) is essential.

The specifications, drawings and the completed bill of quantities or activity schedule will form a part of the eventual Contract.

The SOR must be prepared and included as part of the Bidding Documents. Depending on the size of the contract and the number of pages in each section, it is usual to package Section 6, or each part of Section 6, in a separate volume or volumes. For example, for a large contract, the Technical Specifications, Bills of Quantities and Drawings may each need to be issued in separate volumes. Where separate volumes are issued:

- each volume should be appropriately titled and include the procurement reference number; and

- the relevant page of Section 6 should be included in the Bidding Document for completeness, with a reference to the appropriate volume.

The Statement of Requirements consists of four parts:

1.	Scope of Works

2.	Technical Specifications

3.	Drawings

4.	Bill of Quantities or Activity Schedule

The following notes provide guidance on how to prepare each of these parts.

Scope of Works

This should provide a description of the works, including approximate quantities of major items, which adequately describe the contract scope of work. Additional information that may be included is:

- Site location

- Climate and weather information

- Site investigation studies and reports

- Topographical data

- Site access details

- Details of other ongoing or future works to be carried out by other suppliers during the Contract period

- Information regarding disposal, borrow and quarry areas including royalty payments as applicable

- any other pertinent information regarding the site and the works

A description of approximately 1-2 pages would be appropriate for most contracts.

Technical Specifications

General Notes on Specifications

A set of precise specifications is a prerequisite for Bidders to respond realistically and competitively to the requirements of the works without qualifying or conditioning their bids. In the context of open tendering, the specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of any related plant and services to be procured. The specifications should require that all plant and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract.

Samples of specifications from previous similar projects are useful in this respect. Most specifications are normally written specially by skilled staff or professional consultants engaged for the task. There is no standard set of Specifications for universal application in all sectors and in all countries, but there are established principles and practices which should be followed.

There are considerable advantages in preparing General Specifications for repetitive Works in recognised public sectors, such as highways, bridges, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract. Deletions or addenda could then adapt the General Specifications to the particular Works.

Equivalent Standards and Codes

Care must be taken in drafting specifications to ensure that they are not restrictive. In the specification of standards for goods, materials, and workmanship, recognised international standards should be used wherever possible. Where other particular standards are used, whether Malawian or other standards, the specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, will also be acceptable. The following clause may be inserted in the Special Conditions or Specifications:

“Equivalency of Standards and Codes

Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract. Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified will be accepted subject to the Procuring Entity’s prior review and written consent. Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the Contractor and submitted to the Project Manager at least 28 days prior to the date when the Contractor desires the Project Manager’s consent. In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.”

Terminology

Care must be taken to use the same terminology in the Specifications as used in the remainder of the bidding document, e.g. “Project Manager” and not “Engineer” for the party administering and supervising the contract.

Drawings

Normally the Procuring Entity will insert a list of the contract drawings, including site plans, in this section of the Bidding Document, but will bind and issue the actual drawings in a separate volume. The size will be dictated by the scale of the drawings, which must not be reduced to the extent that details are rendered illegible. If drawings are to be issued in A1 or A2 format, they should be issued in a separate volume. If the drawings are comparatively few in number and can be issued in A4 or A3 size, then the drawings may be included in the Bidding Document itself.

Any notes on the drawings should use the same terminology as used in the rest of the bidding documents.

A simplified map showing the location of the Site in relation to the local geography, including major roads, posts, airports and railroads, is helpful.

The construction drawings, even if not fully developed, must show sufficient details to enable bidders to understand the type and complexity of the work involved and to assist them in pricing the Bill of Quantities.

Bill of Quantities or Activity Schedule

The Procuring Entity will insert:

- a bill of quantities where the contract is to be Admeasurement; or

- an activity schedule where the contract is to be Lump Sum.

The guidance notes below relate primarily to the preparation of a Bill of Quantities. Alternative notes on preparing an Activity Schedule are provided in italics.

Objectives

The objectives of the Bill of Quantities are:

(a)	to provide sufficient information on the specification and quantities of Works to be performed; and

(b)	when a Contract has been entered into, to provide a priced Bill of Quantities for use in the certification and valuation of Works executed.

Works should be itemised in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost. Consistent with these requirements, the layout and content of the Bill of Quantities should be as simple and brief as possible.

The objective of an Activity Schedule is to provide a breakdown of the activities and their associated cost that form the Works to be paid on a lump sum basis. The breakdown is necessary as the basis for certifying interim payments to the Contractor and to assist in valuing any ordered variations.

The works should be broken down by consideration of the nature of each activity, and if applicable by the location. The Procuring Entity will have to determine the degree to which the Works need to be broken down in light of the complexity of the Works and the required time for completion.  Schedules can be provided for each discrete element of the works. If the works require plant and equipment to be provided, separate schedules for the supply only of the plant and equipment may be provided.

Consistent with these requirements the Activity Schedule should be as simple and brief as possible.

General

Care must be taken to use the same terminology in the Bill of Quantities (or Activity Schedule) as used in the remainder of the bidding document, e.g. “Project Manager” and not “Engineer”.

Content

The Bill of Quantities normally has a “Preamble” to introduce explanations and the structure and content of the BOQ.   Detailed sections should follow (for example):

- General Items

- Bills for each type of work or work in each location for example:

  - Earthworks

  - Road Pavements

  - Drainage Structures

  - Retaining Structures

  - Culverts and Bridges

- Daywork Schedules

- Summary Bill of Quantities

The Activity Schedule should generally have a Preamble. While a single Schedule may suffice for some contracts, more than one Schedule may be required for complex works, especially if performed in different locations. For example for a hospital complex these may cover the following:

  - Site Works

  - Utilities

  - Hospital Building Structure

  - Medical Equipment

  - Nurses' Accommodation

  - Doctors' Accommodation

- Daywork Schedules (to be used for any minor variations)

- Summary Activity Schedule

Preamble

The Preamble should indicate the inclusiveness of the unit prices and should state the bases of measurement which have been adopted in the preparation of the Bills of Quantities and which are to be used for the measurement of the works.

The Preamble should state the objective and use of the Activity Schedule and shall contain any pertinent instructions to Bidders regarding the inclusiveness of the prices, completing of the schedules, currency of the prices, correction of errors, treatment of items not priced etc.

Work Items

The items in the Bills of Quantities should be grouped in sections to distinguish between parts of the Works which by nature, location, access, timing or any other characteristic may give rise to different methods of construction, phasing of the work or consideration of cost. General items common to all parts of the works may be grouped as a separate section in the Bills of Quantities.

The items in the Activity Schedule should be grouped in sections to distinguish between parts of the Works which by nature, location, access, timing or any other characteristic may give rise to different methods of construction, phasing of the work or consideration of cost. General items common to all parts of the works may be grouped as a separate section in the Activity Schedule.

Using the example of the hospital complex, the site works and utilities for the whole complex may be grouped into separate Schedules, however the activities required for each of the building should be detailed in a Schedule for that building. For example Sub-Activities for each building could include the following:

  - Excavation

  - Foundations

  - Concrete or Steel Frame

  - Roofing

  - External Cladding and Windows

  - Internal Floors and Walls

  - Internal Finishes

  - Water Supply System

  - Drainage/Sewer System

  - Power System

  - Lighting System

  - Communication/Call/Paging System, etc.

Quantities and Measurement (for Bill of Quantities)

Quantities should be stated in the metric system and computed net from the Drawings and no allowances made for bulking, shrinkage or waste. The methods of measurement, if a standard method is used, should be stated e.g. the UK Institution of Civil Engineer’s “Standard Method of Measurement”. Alternatively, a description of the method of measurement for each work item may be included in the Technical Specification. Clear definition is required to avoid disputes during execution of the contract.

Quantities should be rounded up or down as appropriate to a logical degree of accuracy and spurious accuracy should be avoided.

The following units of measurement and abbreviations are recommended for use.

| Unit | Abbreviation | Unit | Abbreviation |
| --- | --- | --- | --- |
| cubic metre hectare hour kilogram lump sum metre metric ton (1,000 kg) | m3 or cu m ha h kg sum m t | millimetre month number square metre square millimetre week | mm mon nr m2 or sq m mm2 or sq mm wk |

Ground and Excavation Levels (for Bill of Quantities)

The commencing surface should be identified in the description of work involving excavation, boring or piling, for which the commencing level is not the original ground level or the excavated level is not the final finished level. The depths of work should be measured from the commencing level to the excavated surface level as defined by the drawings.

Dayworks Schedule

A Daywork Schedule should generally be included in order to provide a payment mechanism for unforeseen work, outside the items included in the Bill of Quantities (or ordered as a variation by the Project Manager in the case of an Activity Schedule). The Daywork Schedule should normally comprise a list of the various classes of labour, materials, and constructional plant for which basic daywork rates or prices are to be inserted by the Bidder, together with a statement of the conditions under which the Contractor will be paid for work executed on a daywork basis.

Nominal estimated quantities for each item of Daywork should be inserted in the Bill (or Schedule), which is to be priced by each Bidder. This will enable the priced Dayworks to be included in the total bid price and evaluated along with the price for the specified works. The rate to be entered by the Bidder against each basic Daywork item should include the Contractor’s profit, overheads, supervision, and all other charges.

Provisional Sums

A general provision for physical contingencies (e.g. quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities (or Summary Activity Schedule). Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary Bill of Quantities (or Summary Activity Schedule). The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises. Where such provisional sums or contingency allowances are used, the Special Conditions of Contract should state the manner in which they will be used, and under whose authority.

The estimated cost of specialised work to be carried out, or of special goods to be supplied, by other suppliers (refer to Clause 8 of the General Conditions of Contract) should be indicated in the relevant part of the Bill of Quantities (or Activity Schedule) as a particular provisional sum with an appropriate brief description. To provide payment to the Contractor for providing administration, facilities, amenities, attendance, etc., each related provisional sum should be accompanied by an item in the Bill of Quantities (or Activity Schedule) for the Bidders to quote a sum or a percentage fee for services to be provided.

Summary

The Summary should contain a tabulation of each separate Bill (or Schedule), including the Daywork Schedule, and provisional set amounts for contingencies (e.g. for quantities and/or price increases) and a summation for the Total Bid Price.

Sample Bill of Quantities

A Sample Bill of Quantities is provided in Annex 1 to this User Guide to provide an example and format for Procuring Entities. This should be amended as required for each specific Bidding Document.

Guidance Notes on Section 7. General Conditions of Contract

The General Conditions of Contract (GCC) contain standard provisions that have been designed to remain unchanged and to be used without modifying their text. The GCC clearly identify the provisions that may normally need to be specified for a particular bidding process and require that such provisions be introduced through the SCC.

The GCC will form part of any resulting Contract.

Guidance Notes on Section 8. Special Conditions of Contract

The Special Conditions of Contract (SCC) supplement the GCC by modifying conditions applicable to an individual contract, such as payment terms or the name of the project manager. The SCC prevail over the GCC. The Procuring Entity should include all information that the GCC indicate shall be provided in the SCC prior to issuing the Bidding Documents. No SCC Clause should be left blank.

To facilitate the preparation of the SCC, its clauses are numbered with same numbers as the corresponding GCC clauses. This Guide helps the Procuring Entity with inputting all information required and includes a SCC format that summarises all information to be provided.

The SCC will form part of any resulting Contract.

Input of Information to be completed by Procuring Entity

Special Conditions of Contract

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC). Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC Clause Reference | Special Conditions |
| --- | --- |
| GCC 1.1 | The Employer is [insert name and address of Employer, and name of authorised representative]. The Project Manager is [insert name and address of the Project Manager (assuming the Project Manager is an entity) and the name of its authorised representative]. [For smaller contracts, there may be no full-time person acting as project manager. However, the Employer may nominate an authorised spokesman from among its own staff to act as its representative. Where a Employer has appointed a consultant engineer or independent body as the Project Manager, the Employer should be careful not to exercise any of the project manager’s or representative’s powers itself, in order to avoid the risk of conflicting instruction or decisions. The authority of the project manager can be limited in SCC 4.1 if required]. The name and procurement reference number of the Contract is [insert name and number]. The Works consist of [insert brief summary, including relationship to other contracts under the project]. The Site is located at [insert location] and is defined in Drawings Nos.: [insert numbers]. The Start Date shall be [insert date. The intended Start Date and Intended Completion Date may be best specified in terms of days or weeks after the Notice of Acceptance is issued (provided that the site is available to the Contractor at this juncture) rather than stating specific calendar dates. For small contracts, 14 days may be sufficient. For larger contracts, longer will be required. The Start Date is not necessarily the same as any Site Possession Dates]. The Intended Completion Date for the whole of the Works shall be [insert date or period after Notice of Acceptance. If different dates are specified for completion of the Works by section (“sectional completion”), these dates should be listed here.]. |
| GCC 2.3 | The following documents also form part of the Contract: [list any other documents e.g. schedule of information provided by the Contractor]. |
| GCC 3.1 | The language of the Contract is English and the law governing the Contract is that of the Republic of Malawi. [Amend if an alternative language or law is to be used]. |
| GCC 4.1 | The Employer’s specific approval is required for: [insert any decisions for which the Employer’s approval is required]. [e.g. If it is considered that the standard GCC clause gives too much authority to the Project Manager, or there is no full-time engineer as project manager, the following clause may be inserted to limit the authority of the Project Manager and require him to get the Employer’s approval where there are potential additional costs or extensions of time involved: “The Project Manager shall obtain specific approval from the Employer before carrying out any of his duties under the Contract which in the Project Manager’s opinion will cause the amount finally due under the Contract to exceed the Contract Price or will give entitlement to extension of time. This requirement shall be waived in an emergency affecting safety of personnel or the Works or adjacent property.”] [See also the additional optional clauses in the SCC and below.] |
| GCC 8.1 | The Schedule of Other Suppliers [insert “is” or “is not”] part of the Contract. [Ensure the Schedule is attached if required. It is vital to provide all relevant information on other suppliers working on the site. Failure to do so with the result that the Contractor’s work is affected by the work of others, is likely to lead to claims for additional payment]. |
| GCC 9.1 | The Schedule of Key Personnel [insert “is” or “is not”] part of the Contract. [Ensure the Schedule is attached if required]. |
| GCC 13.1 | The minimum insurance covers and deductibles shall be: (a) The minimum cover for insurance of the Works, Plant and Materials is [insert amount]. (b) The maximum deductible for insurance of the Works, Plant and Materials is [insert amount]. (c) The minimum cover for insurance of Equipment is [insert amount]. (d) The maximum deductible for insurance of Equipment is [insert amount]. (e) The minimum cover for insurance of property is [insert amount] (f) The maximum deductible for insurance of property is [insert amount] - The minimum cover for personal injury or death insurance is [insert amount] with no deductible. [The levels of cover and maximum deductible amounts will vary greatly, depending on the nature and value of the works. It is safer to select a higher level of minimum cover and lower deductibles. If in doubt, Procuring Entities should obtain professional advice on acceptable minimum cover limits. The following values are given in US Dollars as a guide only, but may be varied and may be specified in Malawi Kwacha or another appropriate currency: (a-b) minimum cover for loss of or damage to the Works, Plant, and Materials: 110% of the Contract Value with US$50,000 maximum deductible (c-d) minimum cover for loss of or damage to Equipment: 100% of the value of equipment required for the performance of the contract with US$25,000 maximum deductible (e-f) minimum cover for loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract: US$250,000 with US$25,000 maximum deductible (g) minimum cover for personal injury or death. US$500,000 with no deductible.] |
| GCC 14.1 | Site Investigation Report(s) [insert “are” or “are not” and provide details and references of the specific documents if part of the contract] part of the contract. |
| GCC 21.1 | The Site Possession Date shall be: [insert date. If the Site is made available by section, the different dates should be listed here. The date may be best specified in terms of days or weeks after the Notice of Acceptance, rather than stating a specific calendar date. The Site Possession Date must not be later than the Start Date, but may be earlier]. |
| GCC 25.2 | Fees and types of reimbursable expenses to be paid to the Adjudicator are: [insert details of fees and expenses]. [Where no Adjudicator is to be appointed, replace the text with “No Adjudicator is to be appointed under this contract”]. |
| GCC 25.3 | The institution whose arbitration procedures shall be used is: [insert name of institution e.g. UNCITRAL Arbitration Rules] Arbitration shall take place at: [state place e.g. Lilongwe or any other convenient location or delete if arbitration is not applicable] [Where arbitration is not being used, replace the text with “Arbitration shall not be used under this contract and disputes shall be resolved in accordance with GCC 25.1”]. |
| GCC 26.1 | The Appointing Authority for the Adjudicator is: [insert name of Authority. The Appointing Authority should preferably be an independent professional institution or an official (e.g. president) of such an institution. An individual should not normally be nominated]. [For smaller contracts, where the Employer has decided not to appoint an Adjudicator, the text should be replaced with “No Adjudicator is to be appointed under this contract”]. |
| GCC 27.1 | The Contractor shall submit the Programme for the Works within [insert number] days of delivery of the Notice of Acceptance. [For small contracts, 14 days may be sufficient. For larger contracts, longer may be required. Where no Notice of Acceptance is issued, amend to “contract document”]. |
| GCC 27.3 | The period between Programme updates is [insert number] days. [For a short contract, this could be monthly and for longer contracts, every two months. For very small contracts, no updates may be required, in which case the text should be amended accordingly]. The amount to be withheld for late submission of an updated Programme is [insert currency and amount, which should be sufficient to encourage prompt submittal]. |
| GCC 35.1 | The Defects Liability Period is [insert number] days. [The period is normally 365 days (i.e. one year), but may be shortened for smaller contracts or where the risk of defects is considered to be low]. |
| GCC 37.1 | This Contract is a [insert “Admeasurement” or “Lump Sum”, ensuring that it is consistent with clause 13.1 of the Bid Data Sheet] Contract. |
| GCC 44.1(l) | The following events shall also be Compensation Events: [insert list of events or state “none”] |
| GCC 47.1 | The Contract [insert “is” or “is not”] subject to price adjustment in accordance with Clause 47 of the Conditions of Contract, and the following information regarding coefficients [insert “does” or “does not”] apply. [Price adjustment is recommended for contracts which provide for time of completion exceeding 18 months.] The coefficients for adjustment of prices are: (a) For currency [insert type of currency]: (i) [insert percent] percent nonadjustable element (coefficient A). (ii) [insert percent] percent adjustable element (coefficient B). (b) For currency [insert type of currency]: (i) [insert percent] percent nonadjustable element (coefficient A). - [insert percent] percent adjustable element (coefficient B). (c) etc |
| GCC 47.1 | The Index I for Malawi Kwacha will be [insert index. This index will be specified by the Employer in the Bidding Document]. The Index I for the specified international currency will be [insert index. This index will be proposed by the Contractor, subject to acceptance by the Employer]. The Index I for currencies other than Malawi Kwacha and the specified international currency will be [insert indices for each currency]. [These proxy indices will be proposed by the Contractor in his bid and are subject to acceptance by the Employer.] [The Procuring Entity should enter all possible data when drafting the Bidding Document. Data which is specific to the successful bid should be inserted before the Agreement is issued in the conformed contract.] |
| GCC 48.1 | The proportion of payments retained is [insert percent] percent.[This is normally 5 percent, but should not exceed 10 percent]. |
| GCC 49.1 | The rate per day for liquidated damages is [insert percentage] percent of the final Contract Price per day. [If Sectional Completion and Damages per Section have been agreed, the latter should be specified here.] The maximum amount of liquidated damages for the whole of the Works is [insert percent] percent of the final Contract Price. [Usually liquidated damages are set between 0.05 percent and 0.10 percent per day, and the total amount is not to exceed between 5 percent and 10 percent of the Contract Price. It may be seen that if the lower or upper limits of the rate and total amount are applied, the maximum liquidated damages are imposed after 100 days delay. If the rate of 0.05% and the total amount of 10% are assumed, then the maximum liquidated damages are imposed after 200 days delay. The number of days for which the maximum amount of liquidated damages can be paid, as calculated under this clause, affects termination for delaying the works as provided for in Clause 59, Termination in Sub-clause 59.2, Paragraph (g).] |
| GCC 50.1 | The Bonus for the whole of the Works is [insert percent of final Contract Price amount. Insert zero if not applicable. If Sectional Completion and Bonus per Section have been agreed, the latter should be specified here.] of final Contract Price per day. The maximum amount of Bonus for the whole of the Works is [percent] percent of the final Contract Price. |
| GCC 51.1 | The Advance Payment will be equivalent to [insert percentage or state if no advance payment is to be made] percent of the Contract Price and will be paid in the same currencies and proportions as the Contract Price. [Note that the advance payment will actually be made in the proportions of currencies in which the Contract Price is to be paid.] It will be paid to the Contractor no later than [insert period within which payment will be made. This may be best entered as a number of days after the issue of the Notice of Acceptance. In setting the number of days, consideration should be given to the time needed to effect disbursement of funds]. |
| GCC 51.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting [insert number] months after the Start Date and ending [insert number] months after the Start Date. [This Sub-Clause allows the repayment of the advance payment to be made over the whole of the contract period, or alternatively, more stringent repayment terms may be inserted]. |
| GCC 52.1 | The Performance Security shall be for [insert percentage, normally between 5 and 10%] of the Contract Price. |
| GCC 58.1 | The date by which operating and maintenance manuals are required is [insert date or period before or after Date of Completion]. The date by which “as built” drawings are required is [enter date or period before or after Date of Completion]. |
| GCC 58.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required is [insert amount, which should be high enough to encourage timely submission of all documents] Malawi Kwacha. |
| GCC 60.1 | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is: [insert percent. This percentage is intended to compensate the Employer for the additional costs that will be incurred in completing the works following termination. A value between 10 and 20% is considered equitable]. |

Additional Optional Clauses

The following draft clauses are provided for consideration and use by Procuring Entities. They are not intended to be inserted in all Bidding Documents but to be used on an “as needed” basis. Where the clauses are required, they should be inserted into the Special Conditions of Contracts. No changes should be made to the GCC.

| Condition of Contract Clause | Special Conditions of Contract |
| --- | --- |
| 4. Project Manager’s Decisions | If it is desired that the limitations on the Project Managers authority be more clearly defined, then the following may be used instead of the text in the SBD: “The Project Manager shall obtain the specific approval of the Employer in writing before taking any of the following actions specified in the General Conditions of Contract: - Certifying additional costs under Clause 44; - Determining an extension of the Intended Completion Date under Clause 28; - Issuing a variation order under Clause 40 except in an emergency situation as reasonably determined by the Project Manager or if the variation does not increase the Contract Price; - Fixing rates under Clause 40; - Ordering suspension or termination under Clause 59; - [add other limitations and quote clauses]” |
| 7. Subcontracting | The following conditions shall apply to subcontracting: [insert any additional conditions relating to subcontracting e.g. The Contractor shall not impose inequitable or onerous conditions on his appointed subcontractors and shall pay all subcontractors promptly each month, irrespective of the Contractor himself having received payment for work performed by the subcontractor.] |
| 9. Personnel | Semi and Semi-Skilled Labour Only Malawian Nationals shall be employed as unskilled labour. Only Malawian Nationals shall be employed as semi-skilled labour unless the Contractor can demonstrate that no suitably trained Malawian Nationals are available. Rates of Wages and Conditions of Labour The Contractor shall pay rates of wages and observe employment conditions not less favourable than those established for the trade and industry where the work is being carried out. In the absence of any established rates or conditions in the locality, the Contractor shall follow those by other employers for similar trades and industries. Burial of the Dead The Contractor shall be responsible for the transport to his /her home of any expatriate employee or members of their families who may die in Malawi. The Contractor shall be responsible for arrangements for the burial of local employees who may die while engaged upon the Works. Visas and Permits The Contractor shall be responsible for all arrangements and costs of obtaining visas, work permits and other documents for his employees and shall comply with all immigration and residence regulations of Malawi. Repatriation of Employees The Contractor shall be responsible for repatriation of all non-Malawian national employees to their country of residence or to their point of recruitment and for their maintenance until the time of the return. |
| 19. Safety | Safety Officer The Contractor shall employ a full-time qualified Safety Office on site until the Works have been completed. The Safety Officer shall be responsible for compliance with the Contractor’s Site Safety Plan by all employees and shall hold regular safety meetings with all employees. He shall be given authority to halt any unsafe working methods or practices on site. |
| 55. Completion | In order that the Project Manager may certify Completion of the Works, the Works shall be capable of being used for the purpose intended. This shall not necessarily include reinstatement of ground or surfaces unless the reinstatement is required to ensure the safety and convenience of the public or others. |
| Additional Conditions of Contract |  |
| Care of the Environment | The Contractor shall execute the Works in an environmentally friendly manner and shall avoid all unnecessary damage to property and flora. All waste material shall be disposed of in a proper manner to the satisfaction of the Project Manager. |
| Confidentiality | The Contractor shall treat the Contract and everything in connection with it as private and confidential. In particular the Contractor shall not publish or issue any information or photograph concerning the Works and shall not use the site for any commercial purpose except with the consent of the Project Manager and subject to any conditions he may impose. |

Guidance Notes on Section 9. Contract Forms

Section 9 of the Bidding Document contains forms for the Agreement, the Performance Security, and the Advance Payment Security. The purpose of including these forms in the Bidding Document is to notify the Bidders of the type and detail of the Contract they would received in the event of an award. No input is required by the Procuring Entity when drafting the Bidding Document and there is no requirement for Bidders to submit these forms with their bids.

Procuring Entities should consult the section below (Guidance Notes on the Notice of Acceptance) before issuing a Notice of Acceptance.

Agreement

The completed Agreement will form part of any resulting Contract. However, the details to be completed on the Agreement are specific to the successful Bidder and therefore should be left blank for inclusion in the Bidding Document.

After notification of award, the Procuring Entity shall prepare the Agreement using the Agreement Form and send it to the successful Bidder. It is rare that a major works contract is awarded on the basis of only the bid, as negotiations are normally held with the best evaluated Bidder to settle any minor matters arising from the bid or clarifications. It is good practice to conform the contract document in accordance with any agreements reached during negotiations and any modifications during evaluation. The Agreement prepared should therefore incorporate any corrections or modifications to the Bid resulting from corrections of errors, selection of an alternative offer, acceptable deviations, or any other mutually-agreeable changes allowed for in the Conditions of Contract, such as changes in key personnel, subcontractors, scheduling etc. The contracting parties will then sign the conformed document.

This Guide includes an Agreement format that summarises all the information to be provided when preparing the Agreement at contract award stage. Ensure that any legal requirements or conventions regarding the sealing of contracts are followed.

The successful Bidder should sign the Agreement and return it to the Employer.

Performance Security and Advance Payment Security

The Performance Security form should be completed by the financial institution and returned to the Employer, by the Contractor with the signed Agreement. Similarly, if any advance payment is specified in the contract, the Advance Payment Security should be completed by the financial institution and submitted by the Contractor to the Employer with an invoice. Therefore, the Employer is not required to input any information to the security forms.

The security forms are drafts for unconditional (or “on-demand”) bank guarantees, which have the merit of simplicity and of being universally known and accepted by commercial banks. The contracting community, however, strongly objects to this type of Security because the Guarantee can be called (or threatened to be called) by employers without justification. Procuring Entities and Project Managers should recognise the contractual conditions governing nonperformance by the Contractor and should normally act only on the advice of the Project Manager in calling a Performance Guarantee. Any unjustified calling of a Bank Guarantee, or unreasonable pressure exercised by an Employer, would be regarded as contrary to the spirit and basic principles of international procurement. While bank guarantees are often called “bonds”, they should be distinguished from the Performance Bonds customarily used in the USA, which guarantee completion of the works, rather than a stated sum of money.

As the Bidder would be required to complete these Forms in the event of a contract award, the guidance notes in bold between square brackets provide assistance to the Bidder or financial institution and should therefore not be deleted by the Procuring Entity prior to the issue of the Bidding Document.

This User Guide is not intended for Bidders as all information that the Bidder is required to provide should be detailed by the Procuring Entity in the Bidding Document. Therefore the Performance Security and Advance Payment Security forms are not included in this User Guide.

No Input of Information required for inclusion in Bidding Document. Input of Information to be completed by the Procuring Entity at contract award stage.

Agreement

Procurement Reference No: [insert Procurement Reference number]

THIS AGREEMENT made the [insert day] day of [insert month], [insert year], between [insert name of Employer] of [insert address of Employer] (hereinafter called “the Employer”), of the one part, and [insert name of Contractor] of [insert address of Contractor] (hereinafter called “the Contractor”), of the other part:

WHEREAS the Employer is desirous that the Contractor execute [insert brief description of Works] (hereinafter called “the Works”) and the Employer has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of [insert contract price in Malawi Kwacha in words and figures, ensuring it is the same as on any Notice of Acceptance] (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of the Agreement, viz:

(a)	the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c)	the Schedule of Requirements;

(d)	the bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor;

(e)	the Employer’s Notification to the Contractor of award of contract; and

(f)	[list all other documents e.g. Schedule of Key Staff, Site Investigation Reports, etc which are stated in the SCC to form part of the Contract]

3.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract, at the times and in the manner prescribed by the Contract.

- The Contract Price or such other sum as may be payable shall be paid [insert percentage of Contract Price to be paid in Malawi Kwacha] in Malawi Kwacha, [insert percentage of Contract Price to be paid in first foreign currency] in [insert name of first foreign currency] and [insert percentage of Contract Price to be paid in second foreign currency or delete if only two currencies] in [insert name of second foreign currency or delete].

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

Signed by [authorised signatory for the Employer to sign] (for the Employer)

Name: [insert name of authorised signatory] Position: [insert position]

Sealed by the Employer:

Witnessed by:

Name:						Address:

Signed by _____________________________ (for the Contractor)

Name: _____________________________Position: ______________________________

Sealed by the Contractor:

Witnessed by:

Name:			Address:

Guidance Notes on the Notice of Acceptance

The Notice of Acceptance does not form part of the Bidding Document. However, it is the document normally used to accept a bid, and therefore to form a contract, so it is essential that it is used correctly by Procuring Entities. ITB Clause 33 states that a Notice of Acceptance will be the basis for formation of the Contract.

A Notice of Acceptance must not be issued prior to obtaining all required approvals, including from the Internal Procurement Committee and ensuring that sufficient funds have been committed for the contract.

A sample wording for a Notice of Acceptance is included below.

Letterhead paper with PE name and address

To: [Name and address of the Contractor]

[Date]

Dear Sirs,

Notice of Acceptance for [Brief Description of the Works]

This is to notify you that your Bid dated [insert date] for execution of the [name of the Contract and procurement reference number] for the Contract Price of the equivalent of [insert currency and amount in numbers and words], as corrected and modified [delete if no corrections and/or modifications were made] in accordance with the Instructions to Bidders is hereby accepted.

We instruct you to submit to us by [insert date 21 days after receipt] the Performance Security stipulated in the Contract.

You are hereby instructed to proceed with the execution of the said Works in accordance with the Contract documents.

[Where appropriate, a statement on the proposed adjudicator should be included. Recommended wording is given below:

(1)	Where the Contractor disagreed in its Bid with the Adjudicator proposed by the Employer and has accordingly offered another candidate who is acceptable to the Employer, the following should be added:

“We accept that [name proposed by bidder] be appointed as the Adjudicator”.

(2)	Where the Contractor disagreed in its Bid with the Adjudicator proposed by the Employer and has accordingly offered another candidate who is not acceptable to the Employer, the following should be added:

“We do not accept that [name proposed by bidder] be appointed as adjudicator, and by sending a copy of this notice of acceptance to [insert the name of the Appointing Authority], we are hereby requesting [insert the name of the Appointing Authority], the Appointing Authority, to appoint the Adjudicator in accordance with Clause 35.1 of the Instructions to Bidders”.

Yours sincerely,

[Insert name of office and name of officer]	[Insert postal/street address]

Annex 1: Sample Bill of Quantities

Sample	Bill of Quantities

A. Preamble

1.	The Bill of Quantities shall be read in conjunction with the Instructions to Bidders, General and Special Conditions of Contract, Technical Specifications, and Drawings.

2.	The quantities given in the Bill of Quantities are estimated and provisional, and are given to provide a common basis for bidding. The basis of payment will be the actual quantities of work ordered and carried out, as measured by the Contractor and verified by the Project Manager and valued at the rates and prices bid in the priced Bill of Quantities, where applicable, and otherwise at such rates and prices as the Project Manager may fix within the terms of the Contract.

3.	The rates and prices bid in the priced Bill of Quantities shall, except insofar as it is otherwise provided under the Contract, include all Constructional Plant, Labour, supervision, materials, erection, maintenance, insurance, profit, taxes, and duties, together with all general risks, liabilities, and obligations set out or implied in the Contract.

4.	A rate or price shall be entered against each item in the priced Bill of Quantities, whether quantities are stated or not. The cost of Items against which the Contractor has failed to enter a rate or price shall be deemed to be covered by other rates and prices entered in the Bill of Quantities.

5.	The whole cost of complying with the provisions of the Contract shall be included in the Items provided in the priced Bill of Quantities, and where no Items are provided, the cost shall be deemed to be distributed among the rates and prices entered for the related Items of Work.

6.	General directions and descriptions of work and materials are not necessarily repeated nor summarised in the Bill of Quantities. References to the relevant sections of the contract documentation shall be made before entering prices against each item in the priced Bill of Quantities.

7.	Provisional Sums included and so designated in the Bill of Quantities shall be expended in whole or in part at the direction and discretion of the Project Manager.

8.	The method of measurement of completed work for payment shall be in accordance with [insert the name of a standard reference guide, or full details of the methods to be used. The method of measurement should be spelled out precisely in the Preamble to the Bill of Quantities, describing, for example, the allowances (if any) for timbering in excavation, etc. Many national standard reference guides have been prepared on the subject, and one such guide is the Standard Method of Measurement of the U.K. Institution of Civil Engineers.]

9.	Errors will be corrected by the Procuring Entity for any arithmetic errors in computation or summation in accordance with ITB sub-Clause 27.

10.	Rock is defined as all materials which, in the opinion of the Project Manager, require blasting, or the use of metal wedges and sledgehammers, or the use of compressed air drilling for their removal, and which cannot be extracted by ripping with a tractor of at least 150 brake hp with a single, rear-mounted, heavy-duty ripper.

Sample	Bill of Quantities

B. Work Items

1.	The Bill of Quantities usually contains the following part Bills, which have been grouped according to the nature, location or timing of the work:

Bill No. 1:	General Items;

Bill No. 2:	Earthworks;

Bill No. 3: 	Culverts and Bridges;

Bill No. 4	Road Paving Works

Bill No. 5:	etc., as required;

Daywork Schedule; and

Summary Bill of Quantities.

2.	Bidders shall price the Bill of Quantities in Malawi Kwacha only, and shall indicate in the bid the percentage expected for payment in foreign currency or currencies.

Sample	Bill of Quantities

Bill No. 1: General Items

| Item No. | Description | Unit | Quantity | Rate in MWK | Amount in MWK |
| --- | --- | --- | --- | --- | --- |
| 101 | Performance Bond/Guarantee | sum | item | — |  |
| 102 | Insurance of the Works | sum | item | — |  |
| 103 | Insurance of Constructional Plant | sum | item | — |  |
| 104 | Third Party Insurance | sum | item | — |  |
| 105 | Allow for maintenance of Works for 12 months after completion | month | 12 |  |  |
| 106 | —etc.— |  |  |  |  |
| 112 | Provide and equip Project Manager’s offices | nr | 2 |  |  |
| 113 | Maintain Project Manager’s offices for 24 months, including services | month | 24 |  |  |
| 114 | —etc.— |  |  |  |  |
| 121 | Provide diversion road | sum | item | — |  |
| 122 | Provide for traffic control and maintenance of diversion road | month | 24 | — |  |
| 123 | —etc.— |  |  |  |  |
| 132 | Provide for cleaning up the Site on completion —etc.— | sum | item | — |  |
| Total for Bill No. 1 (carried forward to Summary) |  |  |  |  |  |

Sample	Bill of Quantities

Bill No. 2: Earthworks

| Item No. | Description | Unit | Quantity | Rate in MWK | Amount in MWK |
| --- | --- | --- | --- | --- | --- |
| 201 | Excavate topsoil to maximum depth 25 cm and stockpile for reuse, maximum haul distance 1 km | m3 | 9,000 |  |  |
| 202 | Excavate topsoil to maximum depth 25-50 cm, and dispose | m3 | 1,000 |  |  |
| 203 | —etc.— |  |  |  |  |
| 206 | Excavate fill material from cuttings or approved borrow pits, haul up to 1 km, deposit, shape, and compact to fill | m3 | 25,000 |  |  |
| 207 | Excavate rock in cuttings and dispose, any depth | m3 | 250 |  |  |
| 208 | —etc.— |  |  |  |  |
| Total for Bill No. 2 (carried forward to Summary) |  |  |  |  |  |

Sample	Bill of Quantities

Bill No. 3: Culverts and Bridges

| Item no. | Description | Unit | Quantity | Rate in MWK | Amount in MWK |
| --- | --- | --- | --- | --- | --- |
| 301 | Excavate in all materials other than rock from ground level to underside of foundations, maximum depth 5 m, and dispose | m3 | 10,000 |  |  |
| 302 | Excavate in all materials other than rock, depth 5 m to 7.5 m | m3 | 2,500 |  |  |
| 303 | Provisional Item As Item 302, depth 7.5 m to 10 m | m3 | 500 |  |  |
| 304 | —etc.— |  |  |  |  |
| 311 | Concrete class B in abutments | m3 | 2,000 |  |  |
| 312 | —etc.— |  |  |  |  |
| 318 | Mild steel reinforcement in abutments and piers up to 20 mm diameter | t | 37 |  |  |
| 319 | —etc.— |  |  |  |  |
| Total for Bill No. 3 (carried forward to Summary) |  |  |  |  |  |

Sample	Bill of Quantities

C. Daywork Schedule

General

1.	Reference should be made to Clause 53 of the Conditions of Contract. Work shall not be executed on a Daywork basis except by written order of the Project Manager. Bidders shall enter basic rates for Daywork items in the Schedules, which rates shall apply to any quantity of Daywork ordered by the Project Manager. Nominal quantities have been indicated against each item of Daywork, and the extended total for Daywork shall be carried forward as a Provisional Sum to the Summary Total Bid Amount. Unless otherwise adjusted, payments for Daywork shall be subject to price adjustment, if applicable, in accordance with the provisions in the Conditions of Contract.

Daywork Labour

2.	In calculating payments due to the Contractor for the execution of dayworks, the hours for Labour will be reckoned from the time of arrival of the Labour at the job site to execute the particular item of Daywork to the time of return to the original place of departure, but excluding meal breaks and rest periods. Only the time of classes of Labour directly doing work ordered by the Project Manager and for which they are competent to perform will be measured. The time of gangers (charge hands) actually doing work with the gangs will also be measured but not the time of foremen or other supervisory personnel.

3.	The Contractor shall be entitled to payment in respect of the total time that Labour is employed on Daywork, calculated at the basic rates entered by him in the Schedule of Daywork Rates: 1. Labour. The rates shall be all-inclusive and shall cover all direct costs (including the wages paid to such Labour, transportation time, overtime, subsistence allowances, and any sums paid to or on behalf of such Labour for social benefits in accordance with Malawian law), overheads (including superintendence, liabilities, and insurances and allowances to Labour, timekeeping, and clerical and office work, the use of consumable stores, water, lighting, and power; the use and repair of stagings, scaffolding, workshops, and stores, portable power tools, manual plant, and tools; supervision by the Contractor’s staff, foremen, and other supervisory personnel; and charges incidental to the foregoing.) and profit. Payment shall be made in the same currencies and proportion stated in the Contract

Daywork Materials

4.	The Contractor shall be entitled to payment in respect of materials used for daywork at the basic rates entered by him in the Schedule of Daywork Rates: 2. Materials, together with an additional percentage payment on the basic rates to cover overhead charges and profit, as follows:

(a)	the basic rates for materials shall be calculated on the basis of the invoiced price, freight, insurance, handling expenses, damage, losses, etc., and shall provide for delivery to store for stockpiling at the Site. The basic rates shall be stated in local currency, but payment shall be made in the same currencies and proportion stated in the Contract;

(b)	the additional percentage payment shall be quoted by the Bidder and applied to the equivalent local currency payments made under (a) above;

(c)	the cost of hauling materials for use on work ordered to be carried out as daywork from the store or stockpile on the Site to the place where it is to be used will be paid in accordance with the terms for Labour and Construction in this schedule.

Daywork Constructional Plant

5.	The Contractor shall be entitled to payments in respect of Constructional Plant already on Site and employed on daywork at the basic rental rates entered by him in the Schedule of Daywork Rates: 3. Construction Equipment. Said rates shall be deemed to include due and complete allowance for depreciation, interest, indemnity, and insurance, repairs, maintenance, supplies, fuel, lubricants, and other consumables, and all overhead, profit, and administrative costs related to the use of such equipment. The cost of drivers, operators, and assistants shall be included in the rate and no separate payment under the section on Daywork Labour shall be made.

6.	In calculating the payment due to the Contractor for Constructional Plant employed on daywork, only the actual number of working hours will be eligible for payment, except that where applicable and agreed with the Project Manager, the travelling time from the part of the Site where the Constructional Plant was located when ordered by the Project Manager to be employed on daywork and the time for return journey thereto shall be included for payment.

7.	The basic rates for Constructional Plant employed on daywork shall be stated in local currency, but payments to the Contractor will be made in the same currency and proportions stated in the Contract.

Sample	Bill of Quantities

Schedule of Daywork Rates: 1. Labour

| Item No. | Description | Unit | Quantity |  | Rate in MWK | Amount in MWK |
| --- | --- | --- | --- | --- | --- | --- |
| D100 | Ganger | hour | 50 |  |  |  |
| D101 | Labourer | hour | 500 |  |  |  |
| D102 | Bricklayer | hour | 50 |  |  |  |
| D103 | Mason | hour | 50 |  |  |  |
| D104 | Carpenter | hour | 50 |  |  |  |
| D105 | Steelworker Erector | hour | 50 |  |  |  |
| D106 | —etc.— | hour |  |  |  |  |
| D113 | Driver for vehicle up to 5 tons | hour | 100 |  |  |  |
| D114 | Driver for vehicle over 5 tons | hour | 50 |  |  |  |
| D115 | Operator of Heavy Equipment (grader, dozer etc) | hour | 50 |  |  |  |
| D116 | Operator for Light Equipment (compactor, small roller etc. | hour | 50 |  |  |  |
| D117 | —etc.— | hour |  |  |  |  |
|  | Subtotal |  |  |  |  |  |
|  | Total for Daywork: Labour (carried forward to Daywork Summary, p. ) |  |  |  |  |  |

Sample	Bill of Quantities

Schedule of Daywork Rates: 2. Materials

| Item no. | Description | Unit | Quantity |  |  | Rate in MWK | Amount in MWK |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D201 | Cement, ordinary Portland, in bags | t | 20 |  |  |  |  |
| D202 | Mild steel reinforcing bar up to 16 mm diameter to BS 4449 or equivalent | t | 10 |  |  |  |  |
| D203 | Fine aggregate for concrete as specified in Clause | m3 | 100 |  |  |  |  |
| D204 | —etc.— |  |  |  |  |  |  |
| D222 | Crushed road base material | m3 | 50 |  |  |  |  |
|  | Subtotal |  |  |  |  |  |  |
| D299 | Allow percent1 of Subtotal for Contractor’s overhead, profit, etc., in accordance with Paragraph 3(b) above. |  |  |  |  |  |  |
|  | Total for Daywork: Materials (carried forward to Daywork Summary, p. ) |  |  |  |  |  |  |
| 1 To be entered by the Bidder. |  |  |  |  |  |  |  |

Sample	Bill of Quantities

Schedule of Daywork Rates: 3. Constructional Plant

| Item no. | Description | Nominal Quantity (hours) | Basic hourly rate in MWK | Amount in MWK |
| --- | --- | --- | --- | --- |
| D301 | Tracked Excavator: |  |  |  |
| .1 | Up to and including 1 m3 | 50 |  |  |
| .2 | Over 1 m3 to 2 m3 | 40 |  |  |
| .3 | Over 2 m3 | 10 |  |  |
| D302 | Tractor, including bulldozer: |  |  |  |
| .1 | Up to and including 100 kW | 50 |  |  |
| .2 | Over 100 kW to 150 kW | 40 |  |  |
| .3 | Over 150 kW to 200 kW | 20 |  |  |
| D303 | Dump Truck: |  |  |  |
| .1 | 7 to 10 m3 capacity | 40 |  |  |
| .2 | 10 to 15 m3 capacity | 20 |  |  |
| D304 | —etc.— |  |  |  |
| Total for Daywork: Constructional Plant (carried forward to Daywork Summary, p. ) |  |  |  |  |

Sample	Bill of Quantities

Daywork Summary

|  | Amount in MWK |
| --- | --- |
| 1. Total for Daywork: Labour |  |
| 2. Total for Daywork: Materials |  |
| 3. Total for Daywork: Constructional Plant |  |
| Total for Daywork (provisional sum) (carried forward to Bid Summary ) |  |

Sample	Bill of Quantities

Summary of Specified Provisional Sums

| Bill No. | Item No. | Description | Amount in MWK |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 | 2.8 | Provide payment and compensation for crops and damages resulting from construction activities. | 250,000 |
| 3 |  |  |  |
| 4 | 4.32 | Supply and install equipment in pumping station. | 2,500,000 |
| etc. |  |  |  |
| Total for Specified Provisional Sums (carried forward to Grand Summary (B)) |  |  | 2,750,000 |

Sample	Bill of Quantities

Grand Summary

Contract Name:

Contract No.:

| General Summary |  | Amount in MWK |
| --- | --- | --- |
| Bill No. 1: Preliminary Items |  |  |
| Bill No. 2: Earthworks |  |  |
| Bill No. 3: Drainage Structures |  |  |
| —etc.— |  |  |
| Dayworks |  |  |
| Subtotal of Bills No 1 to [number] and Dayworks | (A) |  |
| Specified Provisional Sums included in subtotal of bills | (B) | 2,750,000 |
| Total of Bills less Specified Provisional Sums (A – B) | (C) |  |
| Add Provisional Sum1 for Contingency Allowance | (D) | [sum]2 |
| Bid Price (A + D) | (E) |  |
| Carried forward to Bid Submission Sheet |  |  |
| 1 All provisional sums are to be expended in whole or in part at the direction and discretion of the Project Manager in accordance with Clause 53 of the Conditions of Contract. 2 To be entered by the Procuring Entity. |  |  |